CARIBBEAN NATURAL RESOURCES INSTITUTE (CANARI)

AND

FAO NATIONAL FOREST PROGRAMME FACILITY (NFPF)

### PARTICIPATORY FOREST MANAGEMENT PROJECT:

IMPROVING POLICY AND INSTITUTIONAL CAPACITY FOR DEVELOPMENT

PROPOSED NATIONAL CAPACITY BUILDING STRATEGY

GRENADA

July 2006

# TABLE OF CONTENTS

1.  Project Background								1

2.  Rationale										1

3.  Methodology									1

4.  Capacity Needs Assessment							2

5.  Capacity building strategy under the NFPF project				7

6.  Implementation									9

National Forest Programme Facility

Participatory Forest Management:

Improving policy and institutional capacity for development

PROPOSED NATIONAL CAPACITY-BUILDING STRATEGY

GRENADA

- Project background

This capacity-building strategy for Grenada is an output produced under the regional project entitled “Participatory Forest Management; Improving policy and institutional capacity for development”, which is a three-year project being implemented by the Caribbean Natural Resources Institute (CANARI) with support provided by the Food and Agriculture Organization of the United Nations (FAO) through its National Forest Programme Facility (NFPF). Project countries include Barbados, Dominica, Grenada, Saint Christopher (St. Kitts) & Nevis, Saint Lucia, Saint Vincent & the Grenadines, and Trinidad & Tobago.

The overall goal of the partnership is to support the improvement of the socioeconomic and environmental benefits that can be derived from forest management by analysing, promoting and building capacity for participatory planning and management of forest resources at the regional, national and local levels.

- Rationale

This strategy is a response to the need to build the capacity of stakeholders for participatory policy analysis, policy formulation and forest management through effective training, technical assistance, and regional and cross sectoral dialogue. It is one of the outputs of a consultative process aimed at determining the capacity needs for effective stakeholder participation in the forestry sector. Selected activities are to be supported within the funds available for capacity development in Years 2 and 3 of this project for Grenada.

- Methodology

A consultative process was used to analyse policies and capacity barriers to participation in the forest sector. Research methods included interviews with selected stakeholders and key informants, and a national forest sector stakeholder consultation which brought together representatives from a cross section of backgrounds including the public sector (forest management agencies and other government and public companies in sectors that relate to forestry and forest resources), the private sector (traditional forest users, forest-based businesses and private sector bodies), and civil society (non-governmental and community-based organisations). The main results of the review of national policy and institutional arrangements are contained in a separate report.

The assessment of the capacity of the various stakeholders in forest management was based broadly upon the framework presented in CANARI Guidelines 3, and this information was distilled according to:

  - Identification of target group (according to public sector, civil society sector, private sector).

  - Which groups need capacity built?

  - What capacity needs to be built?

  - How can these needs be met?

- Capacity needs assessment

| Target Group | Barriers to participation | Capacity needs to meet barriers | Major capacity building strategy objectives identified |
| --- | --- | --- | --- |
| All stakeholders | Insufficient awareness of the benefits of participation and of the importance of forests at the level of senior policy-makers Limited involvement of the private sector in forest management Need for a more sophisticated understanding of the concepts and practice of participation, and of the approaches and methods that are best suited to specific conditions | World view Understanding of the linkages between forest management, national development and livelihoods Understanding of the social, economic and financial benefits of participatory approaches Knowledge and skills Development and dissemination of concepts, approaches and methods, particularly in relation to the role of communities and community organisations, opportunities and strategies for forest-based business development, and linkages between forest management and poverty reduction Increased awareness of issues and enhanced capacity to inform and educate among opinion leaders, teachers, media workers and others involved in communication Linkages Formal and informal communication and collaboration channels among government agencies, civil society organisations and the private sector on forest management issues | Mainstreaming of forest management and development in national development processes Participatory review of the national forest policy and harmonisation of policy instruments Awareness campaign focusing on the need for concerted action towards forest management, and for a national consensus to support such action Collaboration with the print and electronic media, with schools and with other civil society actors to stimulate debate around forest management issues Field testing and documentation of approaches and methods suited to specific local conditions |
| Public service |  |  |  |
| Cabinet of Ministers and other senior policy makers | Incomplete understanding and appreciation of forest management issues and their relevance to national development | World view Increased understanding of the linkages between forest management, national development and livelihoods | Awareness campaigns targeted, among others, at policy-makers and senior managers |
| Ministry of Agriculture | Incomplete understanding and appreciation of forest management issues and their relevance to national development Weak linkages with current and potential partners in the private sector, civil society and government | World view Increased understanding of the linkages between forest management, national development and livelihoods Linkages Increased collaboration between the Ministry and its current or potential partners | Awareness campaigns targeted, among others, at policy-makers and senior managers Participatory review of the national forest policy and harmonisation of policy instruments Strengthening of formal and informal linkages between the Ministry and other stakeholders in forest management |
| Forestry Department | Inadequate human and financial resources Insufficient skills to consolidate, institutionalise and sustain participatory approaches | Culture and world view Stronger commitment to participatory approaches and to the development of links between the forestry sectors and other sectors Knowledge and skills Improved skills in participatory forest management Enhanced understanding of the requirements for the identification and promotion of opportunities for sustainable business activities based on forest goods and services Material resources Funding and equipment to maintain presence in the field and support participatory processes Structure Approaches and instruments to formalise co-management arrangements Linkages Formalisation of partnerships between the FNPD and its civil society and private sector partners Development of closer working relationships with governmental and non-governmental agencies involved in supporting business development | Participatory review of the national forest policy and harmonisation of policy instruments Training and sensitisation in social and community development, facilitation, participatory planning, participatory resource mapping and other skills for forestry personnel at all levels Testing, adoption and dissemination of approaches and templates for the design and establishment of collaborative management arrangements |
| NAWASA | Incomplete understanding and awareness of the linkages between forest management and water supply | Knowledge and skills Enhanced understanding of issues among all staff Improved watershed management skills among personnel involved in field management and development work | Training and sensitisation in watershed and participatory forest management |
| Other governmental agencies involved, directly or indirectly, in forest management | Incomplete understanding and appreciation of forest management issues and their relevance to national development | Knowledge and skills Commitment and ability to contribute to processes that link forest management, community development and rural livelihoods | Training and sensitisation in participatory forest management and rural development |
| Civil society |  |  |  |
| National non-governmental development agencies | Resource limitations | Material resources Financial and technical resources required to implement projects and sustain involvement in forestry sector | Enhancement of the project development and fundraising capacity of development agencies Provision of technical and financial support to these agencies |
| Community-based organisations currently or potentially involved in forest-related initiatives | Weak organisational capacity and lack of financial and technical resources Absence of a legal framework to govern their establishment and operation | Knowledge and skills Ability to identify and implement activities that are based on the sustainable use and management of forest resources Material resources Financial and technical resources required to implement projects | Organisational development and strengthening Networking and promotion of direct collaboration among organisations at the community level |
| Private sector |  |  |  |
| All forest resource users and other private sector stakeholders | Lack of capacity and experience to realize the market potential of forest based resources and services Absence of opportunities for formal partnerships with Government in forest management | Knowledge and skills Enhanced understanding of the requirements for the identification and promotion of opportunities for sustainable business activities based on forest goods and services Linkages Improved linkages between the Forestry and National Parks Department, private sector interests and the agencies that are mandated to support business development Formalisation of partnerships between the FNPD and its civil society and private sector partners | Identification, testing and promotion of business opportunities, and of suitable approaches and methods to support and sustain such opportunities |

- Capacity building strategy under the NFPF project

| Target Groups | Strategic Objectives | Activities |
| --- | --- | --- |
| All stakeholders | To review and update the national forest policy, and ensure that it is synchronised with other policy statements and instruments To mainstream forest management and development in national development processes To engage the media in debates and activities focusing on issues of forest management and development | A national forest policy review process, leading to a review of forestry legislation and other statements and instruments Review of the main national development policy instruments to integrate the dimension of forest management and development Field visits and meetings with media personnel to highlight and discuss forestry issues |
| Public sector |  |  |
| Forestry Department | To enhance the conceptual understanding as well as the practice of participatory forest management To further enhance the skills of FNPD staff and to build the commitment and capacity of new staff To develop a framework and a capacity for the design and establishment of collaborative management arrangements | A facilitated two-day seminar to extract and document lessons and methods learned from Grenada’s experience in the formulation and implementation of its national forest policy The provision of documents, training materials and other learning resources to FNPD to ensure that its staff have access to current debates and up-to-date materials on participatory forest management A series of national workshops (senior forestry personnel and their main partners in government, civil society and the private sector), covering such topics as: - conflict management and negotiation - communication - facilitation - advocacy and policy influencing - participatory resource mapping A series of training events for field officers of the FNPD and some of their colleagues in NAWASA and other Departments of the Ministry of Agriculture, covering such topics as: - reporting and basic management skills - problem analysis - mitigation and immediate response - health and safety - communications Participation of staff members of the Department in regional training events focusing on relevant aspects of participatory forest management Participation of at least one senior officer in a regional or international training course on participatory and collaborative resource management Design and testing of a template for collaborative management agreements |
| Ministry of Agriculture | To sensitise the Ministry on the importance and relevance of forestry issues and on the need for adequate resources to support participatory forest management | Involvement of the Ministry, at all levels, in the forest policy review process described above Participation of selected Ministry staff in the series of training workshops mentioned above and below |
| Community Development | To involve development workers in forest management, and to provide them with the basic skills required to support such involvement | A one-day seminar for community development officers, extension personnel from the Ministry of Agriculture and representatives from civil society organisations to illustrate their potential roles in forest management and development |
| NAWASA and other governmental agencies involved, directly or indirectly, in forest management | To involve these agencies and companies in forest management, and to provide them with the basic skills required to support such involvement | Participation of selected representatives from these agencies in the seminars and series of workshops mentioned above |
| Civil society |  |  |
| Community organisations currently or potentially involved in forest management National non-governmental development agencies | To sensitise these organisations to the importance of forestry issues and to the potential benefits they and their communities could gain from being more directly involved in the sector To strengthen the organisations and make them viable over the medium and long term To enable these agencies to design and implement training and capacity-building programmes in participatory forest management for community-based organisations | Collaboration with ART, GRENCODA, G-REP and other partners to explore opportunities for increased involvement of community-based organisations in forestry issues, and to continue processes of organisational strengthening at the local level Provision of information and technical assistance to organisations to link them with possible sources of support Design and conduct of a training-of-trainers programme |
| Private sector |  |  |
| All stakeholders Main water users in industry Farmers and farming communities Craft producers | To develop a locally-relevant set of examples and to build the capacity of private owners and entrepreneurs to realize the market potential of forest based resources and services To enhance the environmental sustainability of existing and prospective business ventures To build their awareness of the value of watershed services To build their awareness of the importance of the forest sector and of the opportunities for community participation To increase collaboration among craft producers and increase their ability to commercialise their products | Conduct of case studies to extract lessons from past experience in forest-based business development, private forestry, and public – private sector partnerships in forest management Communication activities (flyers, seminars, etc.) to disseminate key messages on the relationship between forests, water supply and sustainable economic activity Expansion of on-going environmental education and awareness programmes of the FNPD Consultation with agencies to define a strategy to support craft producers |

- Implementation

The activities proposed in this strategy should be reviewed by all relevant parties, and a final work plan should be developed. The responsibility for the implementation of this work plan should be shared among all key partners, perhaps by establishing an advisory committee led by the FNPD and including representatives of civil society and the private sector. The Ministry of Agriculture should play a lead role in guiding and overseeing the implementation of the strategy, and local expertise and resources should be used to implement specific elements of the strategy as appropriate.

Krishnarayan, V., T. Geoghegan and Y. Renard. 2002. Assessing organisational capacity for participatory natural resource management. CANARI Guidelines Series 3.