CARIBBEAN NATURAL RESOURCES INSTITUTE (CANARI)

AND

FAO NATIONAL FOREST PROGRAMME FACILITY (NFPF)

### PARTICIPATORY FOREST MANAGEMENT PROJECT:

IMPROVING POLICY AND INSTITUTIONAL CAPACITY FOR DEVELOPMENT

PROPOSED NATIONAL CAPACITY BUILDING STRATEGY

ST. VINCENT AND THE GRENADINES

July 2006

# TABLE OF CONTENTS

1.  Project Background								1

2.  Rationale										1

3.  Methodology									1

4.  Capacity Needs Assessment							3

5.  Capacity building strategy under the NFPF project				7

6. Implementation									9

National Forest Programme Facility

Participatory Forest Management:

Improving policy and institutional capacity for development

PROPOSED NATIONAL CAPACITY-BUILDING STRATEGY

SAINT VINCENT AND THE GRENADINES

- Project background

This capacity-building strategy for Saint Vincent and the Grenadines is an output produced under the regional project entitled “Participatory Forest Management; Improving policy and institutional capacity for development”, which is a three-year project being implemented by the Caribbean Natural Resources Institute (CANARI) with support provided by the Food and Agriculture Organization of the United Nations (FAO) through its National Forest Programme Facility (NFPF). Project countries include Barbados, Dominica, Grenada, Saint Christopher (St. Kitts) & Nevis, Saint Lucia, Saint Vincent & the Grenadines, and Trinidad & Tobago.

The overall goal of the partnership is to support the improvement of the socioeconomic and environmental benefits that can be derived from forest management by analysing, promoting and building capacity for participatory planning and management of forest resources at the regional, national and local levels.

- Rationale

This strategy is a response to the need to build the capacity of stakeholders for participatory policy analysis, policy formulation and forest management through effective training, technical assistance, and regional and cross sectoral dialogue. It is one of the outputs of a consultative process aimed at determining the capacity needs for effective stakeholder participation in the forestry sector. Selected activities are to be supported within the funds available for capacity development in Years 2 and 3 of this project for Saint Vincent and the Grenadines.

- Methodology

A consultative process was used to analyse policies and capacity barriers to participation in the forest sector. Research methods included interviews with selected stakeholders and key informants, and a national forest sector stakeholder consultation which brought together representatives from a cross section of backgrounds including the public sector (forest management agencies and other government and public companies in sectors that relate to forestry and forest resources), the private sector (traditional forest users, forest-based businesses and private sector bodies), and civil society (non-governmental and community-based organisations). The main results of the review of national policy and institutional arrangements are contained in a separate report.

The assessment of the capacity of the various stakeholders in forest management was based broadly upon the framework presented in CANARI Guidelines 3, and this information was distilled according to:

  - Identification of target group (according to public sector, civil society sector, private sector).

  - Which groups need capacity built?

  - What capacity needs to be built?

  - How can these needs be met?

- Capacity needs assessment

| Target Group | Barriers to participation | Capacity needs to meet barriers | Major capacity building strategy objectives identified |
| --- | --- | --- | --- |
| All stakeholders | Absence of a formal national policy statement to guide and govern forest management Complexity of forest management issues, especially those that relate to the illegal cultivation of marijuana on public and private lands Limited involvement of private sector and civil society in forest management Lack of locally relevant experience in and diverging understanding of concepts, approaches and methods of participatory forest management | World view Understanding of the linkages between forest management, national development and livelihoods Appreciation of the complexity of current forest management issues and of the need for integrated approaches Knowledge and skills Development and dissemination of concepts, approaches and methods, particularly in relation to the role of communities and community organisations, opportunities and strategies for forest-based business development, and linkages between forest management and poverty reduction Increased awareness of issues and enhanced capacity to inform and educate among opinion leaders, teachers, media workers and others involved in communication Linkages Formal and informal communication and collaboration channels among government agencies, civil society organisations and the private sector on forest management issues | Mainstreaming of forest management and development in national development processes Participatory development of a national forest policy Awareness campaign focusing on the need for concerted action towards forest management, and for a national consensus to support such action Collaboration with the print and electronic media, with schools and with other civil society actors to stimulate debate around forest management issues Field testing and documentation of approaches and methods suited to specific local conditions |
| Public service |  |  |  |
| Ministry of Agriculture | Incomplete understanding and appreciation of forest management issues and their relevance to national development Weak linkages with current and potential partners in the private sector, civil society and government | World view Increased understanding of the linkages between forest management, national development and livelihoods Appreciation of the complexity of current forest management issues and of the need for integrated approaches Linkages Increased collaboration between the Ministry and its current or potential partners | Awareness campaigns targeted, among others, at policy-makers and senior managers Participatory development of a national forest policy Strengthening of formal and informal linkages between the Ministry and other stakeholders in forest management |
| Forestry Department | Absence of a formal national policy statement to guide and govern forest management Insufficient capacity to engage private sector in forest management and in the development of forest products and services Insufficient skills to address the complex social dimension of forest management issues | Culture and world view Stronger commitment to participatory approaches and to the development of links between the forestry sectors and other sectors Knowledge and skills Improved skills in participatory forest management Enhanced understanding of the requirements for the identification and promotion of opportunities for sustainable business activities based on forest goods and services Material resources Funding and equipment to maintain presence in the field and support participatory processes Structure Approaches and instruments to formalise collaborative management arrangements Linkages Formalisation of partnerships between the Forestry Department and its civil society and private sector partners Development of working relationships with governmental and non-governmental agencies involved in supporting business development | Design and implementation of a participatory process to develop a national forest policy Training and sensitisation in social and community development, facilitation and participatory planning for forestry personnel at all levels Testing, adoption and dissemination of approaches and templates for the design and establishment of collaborative management arrangements |
| Utility companies | Incomplete understanding and awareness of the linkages between forest management, water supply and electricity production within these companies | Knowledge and skills Enhanced understanding of issues among all staff Improved watershed management skills among personnel involved in field management and development work | Training and sensitisation in watershed and participatory forest management |
| Community Development Division | Limited involvement of Community Development Officers in forestry issues and processes | Knowledge and skills Enhanced understanding of issues among all staff Commitment and ability to contribute to, facilitate and lead projects and processes that link forest management, community development and rural livelihoods | Training and sensitisation in participatory forest management and rural development |
| Other governmental agencies involved, directly or indirectly, in forest management | Incomplete understanding and appreciation of forest management issues and their relevance to national development | Knowledge and skills Commitment and ability to contribute to processes that link forest management, community development and rural livelihoods | Training and sensitisation in participatory forest management and rural development |
| Civil society |  |  |  |
| National non-governmental development agencies | Limited involvement of development agencies in forestry issues and processes | Knowledge and skills Commitment and ability to contribute to processes that link forest management and rural livelihoods Material resources Financial and technical resources required to implement projects and support local initiatives | Training and sensitisation in participatory forest management and rural development Enhancement of the project development and fundraising capacity of development agencies |
| Community-based organisations currently or potentially involved in forest-related initiatives | Weak organisational capacity and lack of financial and technical resources | Knowledge and skills Commitment and ability to contribute to processes that link forest management, community development and rural livelihoods Material resources Financial and technical resources required to implement projects | Organisational development and strengthening Networking and promotion of direct collaboration among organisations at the community level |
| Private sector |  |  |  |
| All forest resource users and other private sector stakeholders | Lack of capacity and experience to realize the market potential of forest based resources and services Absence of opportunities for formal partnerships with Government in forest management | Knowledge and skills Enhanced understanding of the requirements for the identification and promotion of opportunities for sustainable business activities based on forest goods and services Linkages Improved linkages between the Forestry Department, private sector interests and the agencies that are mandated to support business development Formalisation of partnerships between the Forestry Department and its civil society and private sector partners | Identification, testing and promotion of business opportunities, and of suitable approaches and methods to support and sustain such opportunities |

- Capacity building strategy under the NFPF project

| Target Groups | Strategic Objectives | Activities |
| --- | --- | --- |
| All stakeholders | To develop a national forest policy statement To use the process of policy formulation as a mechanism for awareness raising, mobilisation, community empowerment and networking To mainstream forest management and development in national development processes To engage the media in debates and activities focusing on issues of forest management and development To develop locally relevant experience in and an improved understanding of concepts, approaches and methods of participatory forest management | A national forest policy process, with the following steps: - Development of terms of reference and recruitment of facilitator(s) - Design of participatory process by Forestry Department, Ministry of Agriculture and facilitator(s) - Implementation of the process - Production and dissemination of the policy statement - Implementation of the policy Review of the main national development policy instruments, including the PRSP and the Social Policy, to integrate the dimension of forest management and development Involvement of the media in the policy process mentioned above Field visits with media personnel to highlight and discuss forestry issues Conduct of case studies of selected experiences in participatory forest management Conduct of a series of short (2 hours maximum) seminars on key issues and lessons learned |
| Public sector |  |  |
| Forestry Department | To equip forest officers with appropriate attitudes and adequate skills in participatory forest management To develop a framework and a capacity for the design and establishment of collaborative management arrangements | A series of national workshops to provide training in: - stakeholder identification and analysis - communication skills and stakeholder mobilisation - community profiling and rapid social assessment - conflict management - collaborative management and partnerships Participation of staff members of the Department in regional training events focusing on relevant aspects of participatory forest management Participation of at least one senior officer in a regional or international training course on participatory and collaborative resource management Design and testing of a template for collaborative management agreements |
| Ministry of Agriculture | To sensitise the Ministry on the importance and relevance of forestry issues and on the need for adequate resources to support participatory forest management | Involvement of the Ministry, at all levels, in the forest policy process described above Participation of selected Ministry staff in the series of training workshops mentioned above |
| Community Development Division | To involve development workers in forest management, and to provide them with the basic skills required to support such involvement | A one-day seminar for all community development officers and representatives from civil society organisations (see below) to illustrate their potential roles in forest management and development Participation of selected community development officers and representatives from civil society organisations (see below) in the series of workshops mentioned above |
| Public utility companies and other governmental agencies involved, directly or indirectly, in forest management | To involve these agencies and companies in forest management, and to provide them with the basic skills required to support such involvement | Participation of selected representatives from these agencies in the seminars and series of workshops mentioned above |
| Civil society |  |  |
| Community organisations currently or potentially involved in forest management National non-governmental organisations with the potential to support local initiatives and involvement in forest management | To develop collaboration and enhance networking among community-based organisations currently or potentially involved in forest management To strengthen the organisations and make them viable over the medium and long term To involve national non-governmental organisations in forest management, and to provide them with the basic skills required to support such involvement | Design and implementation of a process aimed at developing an informal network among these organisations A series of workshops with interested organisations, focusing on priority aspects of organisational development, including: - organisational management - proposal writing - project management - financial management - communication, advocacy and networking - nursery and watershed management - identification and implementation of income-generating projects Provision of information and technical assistance to organisations to link them with possible sources of support A one-day seminar for representatives from civil society organisations and community development officers (see above) to illustrate their potential roles in forest management and development |
| Private sector |  |  |
| All stakeholders | To develop a locally-relevant set of examples and to build the capacity of potential entrepreneurs to realize the market potential of forest based resources and services To enhance the environmental sustainability of existing and prospective business ventures | Conduct of case studies to extract lessons from past experience in forest-based business development Participatory formulation of a set of voluntary standards and guidelines for business operations in the two main industries, namely water bottling and ecotourism |

- Implementation

The activities proposed in this strategy should be reviewed by all relevant parties, and a final work plan should be developed. The implementation of this work plan should place a central responsibility in the hands of the Integrated Forest Management and Development Programme, since its purpose is precisely to promote participatory forest management through conflict resolution, alternative livelihoods and local involvement in governance. The Ministry of Agriculture should play a lead role in guiding and overseeing the implementation of the strategy, and local expertise and resources should be used to implement specific elements of the strategy as appropriate.

Krishnarayan, V., T. Geoghegan and Y. Renard. 2002. Assessing organisational capacity for participatory natural resource management. CANARI Guidelines Series 3.